## To-do list
To-do list |  | Completed by: | Edwin Velazquez
|  | Deadline: | 2016-04-30
Done? | Revenge | Due By | Notes
Yes | Planning | 2016-04-01 | Edwin
No | Create Tasks | 2016-04-04 | Edwin
No | Task a | 2011-04-18
No | Decompose Tasks | 2016-04-06 | All
Tasks
No | Get Background(s) | 2016-04-08
No | Get Sprites(s) | 2016-04-08
No | Get Music | 2016-04-10 | Edwin
No | Get Sound effects | 2016-04-12 | Edwin
No | Get Voiceovers? | 2016-04-12 | Edwin
No | Main Class | 2016-04-12
No | Biker class | 2016-04-12
No | Skateboard class | 2016-04-14
No | Car class | 2016-04-14
No | Truck class | 2016-04-16
No | Bicycle class | 2016-04-18
No | Player movement | 2016-04-20
No | Enemy movements | 2016-04-22
No | Scrolling | 2016-04-24
No | Weapons | 2016-04-26
No | Scoring | 2016-04-28
No | Game controls | 2016-04-30
No | Merge classes | 2016-04-15
No | Levels? | 2016-04-17
No | Testing | 2016-04-19
Note on D4: Conditional Formatting shows icons based on how soon an item is due. Red - Past due Yellow - Due within one week Green - Due in more than one week