## To-do list
To-do list |  | Completed by: | Edwin Velazquez
|  | Deadline: | 2016-04-30
Done? | Revenge | Due By | Notes
Yes | Planning | 2016-04-01 | Edwin
Yes | Create Tasks | 2016-04-04 | Edwin
No | Task a | 2011-04-18
No | Decompose Tasks | 2016-04-06 | All
Tasks
Yes | Get Background(s) | 2016-04-08 | Edwin
Yes | Get Sprites(s) | 2016-04-08 | Edwin
Yes | Get Music | 2016-04-10 | Edwin
Yes | Get Sound effects | 2016-04-12 | Edwin
No | Get Voiceovers? | 2016-04-12 | Edwin
No | Main Class | 2016-04-12
No | Biker class | 2016-04-12 | Edwin
No | Skateboard class | 2016-04-14 | Josue
No | Car class | 2016-04-14 | Josue
No | Truck class | 2016-04-16
No | Bicycle class | 2016-04-18
No | Player movement | 2016-04-20 | Josue
No | Enemy movements | 2016-04-22 | Josue
No | Scrolling | 2016-04-24
No | Weapons | 2016-04-26
No | Implement Sound | 2016-04-27 | Edwin
No | Scoring | 2016-04-27
No | Game controls | 2016-04-28 | Josue
No | Merge classes | 2016-04-29
No | Levels? | 2016-04-30
No | Testing | 2016-04-30
Note on D4: Conditional Formatting shows icons based on how soon an item is due. Red - Past due Yellow - Due within one week Green - Due in more than one week